WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 3

# Lab 3: Lifecycle Selection & Increment Plan

Formative (ungraded) · Moodle-enabled · output feeds Task 2 Part 2 directly

| Item | Details |
| --- | --- |
| Linked to | Week 3 lecture — Software Process Models (ULO2, ULO3) |
| Work mode | Individually, on the SAME client scenario you chose for Task 2 |
| Time | About 90 minutes |
| Submission | Completed worksheet uploaded to Moodle AND committed to week03/ in your Git portfolio |
| Why it matters | Section C of this worksheet is a first draft of Task 2 section 2.3 (work schedule). Do it properly now and Week 8 gets much easier. |

## Purpose

In the lecture you met six ways to organise the same four activities, and six questions that decide which one fits. Now you apply that decision to a real client — yours. There is no single correct model; the marks in Task 2 (and the exams) come from the quality of your justification.

## Part A — Apply the six selection questions (30 min)

For each question, answer for YOUR client scenario (Kina Ridge Primary School or Waghi Valley Produce Cooperative) and say what it pushes you toward.

| # | Selection question | Your answer for this client | Pushes toward… |
| --- | --- | --- | --- |
| 1 | How well understood are the requirements? | Most requirements are known (fee payments, receipts, balances, reports), but some details such as instalment policies and reporting requirements may change after discussions with the school. | Incremental / Agile |
| 2 | Can the client engage continuously? | Yes. The bursar and headmaster can regularly review the system and provide feedback during development. | Agile / Incremental |
| 3 | What does the contract or funding demand? | The school wants a reliable system within its budget. There are no strict government regulations requiring a fixed development process. | Incremental |
| 4 | How big is the team, and where is it? | The project is completed by one student developer working closely with the school in Port Moresby. | Incremental |
| 5 | What is the cost of failure? | High. Incorrect fee records or lost payment information could affect parents, students, and the school's finances. | Waterfall elements (careful testing) |
| 6 | How fast must value appear for this client? | The school needs a working payment recording system as soon as possible to replace manual record keeping. | Incremental Delivery |

## Part B — Choose and justify (15 min)

Chosen lifecycle: Incremental Development Model with Waterfall practices for testing and documentation  (may be a blend — say so explicitly)

In 150–200 words, justify the choice using your Part A answers. Name at least one factor that argues AGAINST your choice, and say how you will manage it.

The Incremental Development Model is the most suitable lifecycle for Kina Ridge Primary School because the system can be delivered in small, useful stages. The school urgently needs a digital system to replace manual fee records, so providing a working payment recording system first gives immediate value. The bursar and headmaster are available to review each increment and suggest improvements before the next stage is developed. This approach reduces the risk of building features that do not meet the school's needs. Some project activities, such as documentation, testing, and final validation, will follow Waterfall practices to ensure that financial records are accurate and reliable before deployment. Since payment information is sensitive, careful testing is essential. One factor against using Incremental Development is that changes requested after each release may increase development time. This risk will be managed by clearly defining the scope of each increment and obtaining client approval before moving to the next stage. Combining incremental delivery with structured testing provides both flexibility and reliability.

Blends are professional, not a cop-out. "Incremental delivery internally, phase milestones reported to the board" is a legitimate and common answer in PNG work — provided you explain how the two fit together.

## Part C — Plan three increments (35 min)

Split your client's system into three increments. Increment 1 must be genuinely usable on its own — something the client could put to work the day you hand it over.

| Increment | What it delivers | Why THIS order (risk or value?) | Rough duration & why |
| --- | --- | --- | --- |
| 1 | Student registration, fee payment recording, payment receipts, and outstanding balance. | This provides immediate value because the school can begin recording payments electronically from the first release. | 3 weeks – Core features require database design and testing. |
| 2 | Instalment payment management, payment history, parent search, and reporting for the bursar. | Builds on the payment system and improves financial management. | 2 weeks – Uses data collected in Increment 1 |
| 3 | Headmaster reports, refund management, family discounts, user accounts, backup and recovery. | Administrative features are less urgent but improve long-term system management. | 2 weeks – Final enhancements and system testing. |

### C4. Delivery-condition check

For each increment, note one PNG delivery condition that affects when or how you can deliver it (client travel, power, connectivity, harvest or school-term timing, committee approval cycles).

Condition notes

Increment PNG Delivery Condition

- Power outages require the system to work offline and allow data entry without internet access. - School staff may only be available during school holidays or weekends for training and feedback. - Final approval must be obtained from the Board of Governors before the system is fully implemented.

## Part D — Reflect (10 min)

- If the client suddenly demanded ALL three increments by the same original deadline, which corner of the dependency triangle would you push back on, and what exactly would you say to them?

- Which of your three increments is most likely to change after the client sees increment 1? What does that tell you about how firmly to specify it now?

Your answers

### 1. If the client suddenly demanded all three increments by the original deadline, which corner of the dependency triangle would you push back on? I would negotiate the scope of the project. I would explain to the client that delivering all features within the same deadline could reduce the quality and reliability of the system. I would recommend releasing the essential payment functions first and scheduling the remaining features for later updates. This ensures the school receives a reliable system without compromising quality.

### 2. Which of your three increments is most likely to change after the client sees Increment 1? What does that tell you about how firmly to specify it now? Increment 2 is the most likely to change because the bursar may request different report formats, instalment rules, or payment history features after using the first version of the system. This indicates that the requirements for Increment 2 should remain flexible and be refined based on user feedback from Increment 1, rather than being specified in complete detail from the beginning.

## Submitting

- Save as Lab3_<YourName>.docx and upload to Moodle → Week 3 → Lab 3.

- Copy it into week03/ in your portfolio and commit:

git add week03/ && git commit -m "Add Lab 3 lifecycle selection and increment plan"

- Keep it open when you start Task 2 Part 2 — Parts B and C become sections 2.3 and 2.4.