Name: Justin Albert

ID: 00110

WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 6

Estimation Workshop

In session · individual work on YOUR Task 2 client · output IS Task 2 sections 2.1–2.3

| Item | Details |
| --- | --- |
| Linked to | Week 6 lecture — Estimation & the Work Schedule (ULO3) |
| Bring | Your Week 5 architecture (Lab 4) and your Week 3 increment plan (Lab 3) |
| Time | 120 minutes: 30 breakdown · 35 estimate · 20 calendar · 25 schedule · 10 commit |
| Submission | This worksheet to Moodle AND committed to week06/ in your Git portfolio |
| Counts toward | Nothing directly — but it drafts 15 of the marks in Task 2 |
| You cannot estimate what you have not designed. Work from your Week 5 package and deployment diagrams: each component is a natural work item. If you did not complete Lab 4, do a rough breakdown from your SRS instead and note that as an assumption. |  |

Part A — Break down Increment 1 (30 min)

Take Increment 1 only from your Week 3 plan — the slice that is independently usable. Decompose it until every task is between 2 and 16 hours. Aim for 8–12 tasks.

Do not forget: unit tests · durability/failure testing · code review · client review and rework · documentation · installation and handover. In the worked example these came to 39% of the total.

Part B — Estimate each task (35 min)

For each task give three numbers in hours. O = everything goes right. M = a normal day. P = the realistic bad case (about one time in twenty), not the apocalypse.

E = ( O + 4M + P ) ÷ 6          SD = ( P − O ) ÷ 6

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 3: Database design | 6 | 8 | 12 | 8.33 | 1.00 | It depends on power at the campus. |
| 2 | 4: Interface design | 5 | 8 | 12 | 8.17 | 1.17 | Implement standard styling components. |
| 3 | 5: User access | 4 | 6 | 9 | 6.17 | 0.83 | Save time by using built-in security frameworks. |
| 4 | 6: Student/fee module | 8 | 12 | 18 | 12.33 | 1.67 | Finalize user registry by assuming important fields. |
| 5 | Overhead: | 3 | 5 | 10 | 5.50 | 1.17 | Important for automated logic verification. |
| 6 | Overhead: | 2 | 4 | 8 | 4.50 | 1.00 | During the sudden drops of network simulates system behaviour. |
| 7 | Overhead: | 2 | 4 | 8 | 4.50 | 1.00 | Peer reviewer available within 24 hours. |
| 8 | Overhead: | 4 | 6 | 12 | 6.67 | 1.33 | Requires the client of the project to have access on campus. |
| 9 | Overhead: | 3 | 5 | 8 | 5.17 | 0.83 | Written simultanesouly alongside component coding. |
| 10 | Overhead: | 2 | 4 | 8 | 4.50 | 1.00 | Local hosting setup for the early user. |

Total E = 65.84 hours         Combined SD = √(sum of SD²) = 3.51 hours

Statistical Calculations:

- Total Expected Time (E): 65.84 hours (for Increment 1 only)

- Combined Standard Deviation = √ 1002 + 1.172 + 0.832 + 1.672 + 1.172 + 1.002 + 1.002 + 1.332 + 0.832 + 1.002 = 3.51 hours

Note: the combined SD is NOT the sum of the SDs — square each one, add them, then take the square root. Risks partly cancel out.

Part C — Convert to a calendar (20 min)

| Question | Your answer |
| --- | --- |
| How many PRODUCTIVE hours per week can you truly give this project? (Count your other units.) | 12 hours (Realistic target for 4 other university units, lectures, assignments, projects, labs and group tasks). |
| Total E ÷ productive hours per week = how many weeks? | 54.17 / 12 = 4.5 weeks. |
| Same calculation using E − SD and E + SD → your honest range | 4.2 to 4.8 weeks. |
| Which PNG factors will stretch this? (client availability, travel, power, term dates, holidays) | Power outages |
| Adjusted finish, stated as a range | 5.5 to 6.5 weeks. |

Part D — Build the schedule (25 min)

Lay out all three increments with client-visible milestones. A milestone must be something your client could verify themselves — “the bursar records a real payment and prints a receipt”, never “backend complete”.

| Increment | What it delivers | Milestone the client can see | Weeks |
| --- | --- | --- | --- |
| 1 | User authentication and secure administration dashboard. | The client securely logs into portal using a password and successfully views empty statistics on the dashboard. | 1 to 6 weeks |
| 2 | Important feature: Student record creation and profile management. | The registrar inputs a real student profile, saves it, and can search and display it on screen. | 7 to 10 weeks |
| 3 | Payment tracking module and billing reports. | The school bursar inputs a cash payment, click save, and the system prints out an official, sequentially numbered receipt. | 11 to 14 weeks |

Part E — Commit (10 min)

- Put this worksheet into week06/ in your portfolio.

git add week06/

git commit -m "Add increment 1 estimate and delivery schedule"

Reference — the worked example from the lecture

Kina Ridge fee system, Increment 1. Use it to check your arithmetic method, not to copy numbers.

| Task | O | M | P | E | SD |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project + repo setup | 2 | 3 | 6 | 3.33 | 0.67 |  |
| Data model + local database | 4 | 6 | 12 | 6.67 | 1.33 |  |
| Payment entry screen | 6 | 10 | 20 | 11.00 | 2.33 | widest spread |
| Receipt numbering + printing | 4 | 8 | 16 | 8.67 | 2.00 |  |
| Authorisation (bursar / head) | 3 | 5 | 10 | 5.50 | 1.17 |  |
| Unit tests | 4 | 6 | 10 | 6.33 | 1.00 | non-coding |
| Power-failure durability test | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| Client review + rework | 3 | 6 | 14 | 6.83 | 1.83 | non-coding |
| Install + handover at school | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| TOTAL | 30 | 52 | 108 | 57.67 | 4.58 |  |

Sum of “most likely” alone = 52.0 h. PERT expected = 57.7 h — the 11% gap is optimism made visible. Honest range = 53–62 h. Non-coding work = 22.5 h, 39% of the job. At 10 productive hours a week that is about 5.8 weeks.