WESTERN PACIFIC UNIVERSITY

CMN224/CMP224 Software Engineering

TASK 2: REQUIREMENTS & ESTIMATION REPORT

Scenario A: Kina Ridge Primary School Fee-Tracking System

Name: Justin Albert
Student ID: 00110
Lecturer: Mr. S. Hombiku
Due Date: Week 8

Part 1: Concise Software Requirements (SRS)

  - Purpose and Scope

1.1.1 Purpose

Kina Ridge Primary School is a private institution in Port Moresby with around 450 students enrolled. The school is currently monitoring fees using a notebook and Excel. Parents can choose to pay via cash, bank transfer, or mobile transaction, and some payments might be split into installments.
The current approach limits the capacity to find accurate payment records, identify students with outstanding fees, and generate trustworthy receipts.
The goal of the proposed Kina Ridge Primary School Fee-Tracking System is to create a simple and reliable way to track fees and payments, manage balances, issue receipts, and produce essential reports.

1.1.2 In Scope

The first version of the system will include:

- Student and fee records.

- Payment recording.

- Cash, bank deposit and mobile-transfer payment methods.

- Instalments payments

- Automatic outstanding-balance calculation.

- Payment history and student search.

- Receipt generation and printing.

- Arrears identification.

- Basic management reports.

- User login and assess control

- Basic audit trial and data backup.

1.1.3 Out of Scope

The following features are outside the scope of the first version:

- Student attendance or examination management.

- Payroll or human-resource management.

- Online teaching.

- School timetable management.

- Full accounting software.

- Direct bank or mobile transfer integration.

- Online payments.

- Parent mobile transfers or SMS services.

- Stock management.

By keeping all these features outside the first release helps control project scope, time and cost.

  - Business context and Stakeholders

Kina Ridge Primary School has an enrollment of approximately 450 students. Currently, fee information is divided between a notebook and an Excel file. Payments may be processed via different methods and can be completed in parts.
The bursar is the main user, so the system must be simple and efficient for daily tasks. The reports are primarily needed by the principal and board. Parents and guardians need accurate records, since incorrect payment information may lead to disputes.

| Stakeholder | Role | Main Need |
| --- | --- | --- |
| Bursar | Main system user | Needs to quickly record payments, check balances and issue receipts. |
| Office assistants | Supporting users | Need to search student records and help record or confirm payments. |
| Head teacher | Management user | Needs accurate reports about payments and fee arrears. |
| School board | Management/oversight | Needs term summaries/reports to understand the school's fee collection position. |
| Parents/guardians | Payers | Need accurate records and trustworthy receipts for payments made. |
| Students | Beneficiaries of school administration | Need their fee records to be correctly maintained. |
| School management. | Business owner. | Needs a reliable system that reduces errors and missing records. |
| System administrator | Technical/support role | Needs to manage user access and backups. |

  - Functional Requiremtns

Functional requirements describe what the system shall do.

The requirements below use MoSCoW priorities:

- Must - important for the first release.

- Should - important but the system can operate without it initially.

- Could - useful if time and budget allow.

- Won't - purposily excluded from the first release.

| ID | Functional Reequirement | Priority |
| --- | --- | --- |
| FR-01 | The system will enable an authorized user to generate a student fee record. | Must |
| FR-02 | The system will keep the student's name, student ID, and associated class details. | Must |
| FR-03 | The system must enable an authorized user to record the fees that a student owes. | Must |
| FR-04 | The system shall allow authorised users to record cash payments. | Must |
| FR-05 | The system must enable authorised users to record bank deposit payments. | Must |
| FR-06 | The system shall allow authorised users to record mobile-transfer payments. | Must |
| FR-07 | The system shall allow a payment to be recorded as an installment. | Must |
| FR-08 | The system shall automatically calculate the remaining balance after a payment is recorded. | Must |
| FR-09 | The system shall display the payment history for an individual student. | Must |
| FR-10 | The system shall generate a unique receipt/reference number for each recorded payment. | Must |
| FR-11 | The system shall allow authorised users to print a payment receipt. | Must |
| FR-12 | The system shall allow users to search for a student by student ID or name. | Must |
| FR-13 | The system shall identify students with outstanding fee balances. | Must |
| FR-14 | The system shall allow authorised users to correct an incorrectly entered transaction while keeping a record of the change. | Should |
| FR-15 | The system shall produce a report showing total fees collected for a selected period. | Should |
| FR-16 | The system shall produce a report showing students with outstanding balances. | Should |
| FR-17 | The system shall produce a term summary report for school management and the board. | Should |
| FR-18 | The system shall allow authorised users to view daily payment totals. | Should |
| FR-19 | The system could provide simple charts showing fee collection and arrears. | Could |
| FR-20 | The system could allow export of selected reports to a common file format such as PDF or spreadsheet format. | Could |
| FR-21 | The system shall not provide payroll, attendance or student examination management in the first release. | Won’t |

Key Functional Priorities

The most important functions are payment recording, balance calculation, receipts and arrears information. These functions are prioritised as Must because they directly address the main problems described by the client. More advanced functions such as charts are lower priority because they are useful but are not necessary for the school to manage fees.

  - Non-functional Requirements

Non-functional requirements describe how well the system must work and the conditions under which it must operate.

The requirements below specifically consider the conditions at Kina Ridge Primary School.

| ID | Non-Functional Requirement | Measure/Reason |
| --- | --- | --- |
| NFR-01 | The system shall save a payment before showing it as successfully recorded. | No unsaved payment shall appear as successful. |
| NFR-02 | The system shall display a student record within 3 seconds under normal conditions. | Staff should not have to wait a long time for records. |
| NFR-03 | A trained bursar shall be able to record a normal payment within 2 minutes, excluding printer delays. | Supports fast daily payment work. |
| NFR-04 | The system shall require user login before financial records can be accessed. | Unauthorised users cannot access records. |
| NFR-05 | Only authorised users shall change payment records. | Access is controlled by user role. |
| NFR-06 | The system shall record the user and date for important changes to financial records. | Changes can be traced. |
| NFR-07 | Saved transactions shall remain available after a power interruption and restart. | No loss of successfully saved transactions. |
| NFR-08 | The system shall operate on the school's existing office laptop. | No specialised computer required. |
| NFR-09 | The system shall support printing of receipts using the school's available printer. | Printed receipts are required for trustworthy payment evidence.. |
| NFR-10 | Essential record entry should remain possible during temporary internet loss where the chosen technical solution supports it. | The system should not depend unnecessarily on continuous internet access. |
| NFR-11 | Financial records shall be backed up at least once per working day. | Reduces the risk of losing financial records. |
| NFR-12 | The system shall use simple labels and forms suitable for trained office staff. | The bursar and office assistants are the main users. |
| NFR-13 | Money values shall be displayed in Papua New Guinea kina. | Currency shown as K/PGK. |
| NFR-14 | The system shall prevent a user from recording a payment with an invalid or zero amount. | Reduces data-entry errors. |

PNG Delivery Conditions

The school experience weekly power outages, thus stored records must endure these power disruptions. There is just one primary office laptop, so the system must be compatible with the current hardware. A printer is ready and needs to enable receipt printing.
WiFi typically functions, but ongoing internet availability shouldn't be considered assured. The system should accurately represent the actual payment methods of the school by accommodating cash, bank transfers, mobile payments, and installment plans.

  - Constraints and Business Rules

Constraints

The following constraints are based on the client scenario:

- The school has approximately 450 students.

- The school currently has one office laptop for the main fee-recording work.

- A printer is available.

- Power cuts occur weekly.

- WiFi is usually available but should not be assumed to be available at all times.

- The school currently uses an exercise book and Excel.

- Payments may be made using cash, bank deposits or mobile transfer.

- Parents may pay fees in instalments.

- The first release has a limited project scope.

- The project should use existing school equipment where practical.

Business Rules

BR-01: Every payment shall belong to a valid student record.

BR-02: Every payment shall have a date.

BR-03: Every payment shall have a payment method.

BR-04: The payment methods supported in the first release shall be cash, bank deposit and mobile transfer.

BR-05: A student may have multiple payments because fees can be paid in instalments.

BR-06: The student's outstanding balance shall be calculated from the fee amount and recorded payments.

BR-07: The system shall not allow an invalid payment amount to be recorded.

BR-08: Every successful payment shall receive a unique receipt/reference number.

BR-09: A payment record shall not be silently deleted after it has been used for financial reporting.

BR-10: Corrections to financial records shall be restricted to authorised users.

BR-11: Important changes to financial records shall be traceable to the user who made the change.

BR-12: Only authorised staff shall access student financial information.

BR-13: A payment shall not reduce the student's balance below zero unless the school later approves an overpayment policy.

BR-14: The first release shall not include full accounting, payroll or student management functions.

  - Glossary

| Term | Definition |
| --- | --- |
| Arrears | Fees that remain unpaid after they are due. |
| Balance | The amount a student still owes. |
| Bursar | Staff member responsible for school financial records. |
| Instalment | A partial payment of a larger fee amount. |
| Mobile money | Payment made through a mobile-money service. |
| Receipt | Evidence that a payment has been recorded. |
| Payment reference | An identifier used to identify a payment. |
| Functional requirement | Something the system must do. |
| Non-functional requirement | A condition describing how the system must operate. |
| Stakeholder | A person or group affected by the system. |
| MoSCoW | Method for prioritising requirements as Must, Should, Could or Won't. |
| Audit trail | Record of important changes showing who made them and when. |
| Backup | A copy of data used to recover lost information. |
| Scope | The work and features included in the project. |

Part 2 - Estimate & work schedule

2.1 Task Breakdown

The project is divided into smaller tasks so that each part can be estimated. The breakdown also helps identify dependencies between activities.

| ID | Task | Main Work |
| --- | --- | --- |
| T1 | Requirements | Confirm needs and finalise SRS. |
| T2 | Planning | Plan system structure and technical approach. |
| T3 | Database design | Design student, fee, payment and user data. |
| T4 | Interface design | Design simple user screens. |
| T5 | User access | Develop login and permissions |
| T6 | Student/fee module | Develop student and fee records. |
| T7 | Payment module | Develop cash, bank, mobile-money and instalment recording. |
| T8 | Balance/receipt functions | Develop balance calculation and receipts. |
| T9 | Search/reports | Develop search, history, arrears and management reports. |
| T10 | Audit/backup | Develop change tracking and backup process. |
| T11 | Testing | Test functions, calculations, security and recovery. |
| T12 | User acceptance | School staff test the system. |
| T13 | Deployment/training | Install system, train users and hand over. |

Part 2 - Estimate & work schedule

2.1 Task Breakdown

The project is divided into smaller tasks so that each part can be estimated. The breakdown also helps identify dependencies between activities.

| ID | Task | Main Work |
| --- | --- | --- |
| T1 | Requirements | Verify requirements and complete SRS. |
| T2 | Planning | Blueprint system framework and technological strategy. |
| T3 | Database design | Design pupil, charge, transaction and user information. |
| T4 | Interface design | Create straightforward user interfaces. |
| T5 | User access | Create login and access rights |
| T6 | Student/fee module | Create student and fee records. |
| T7 | Payment module | Create records for cash, bank, mobile-money, and installment transactions. |
| T8 | Balance/receipt functions | Establish a process for tracking changes and creating backups. |
| T9 | Search/reports | Test functionalities, computations, safety, and restoration. |
| T10 | Audit/backup | School personnel evaluate the system. |
| T11 | Testing | Set up the system, train users, and transfer ownership. |
| T12 | User acceptance | School staff test the system. |
| T13 | Deployment/training | Install system, train users and hand over. |

2.2 Time Estimates, Assumptions and Reasoning

Estimation Method

A three-point estimation approach is used for this initial estimate. For each major task, three values are considered:

- Optimistic (O): The tasks proceeds without issues.

- Most likely (M): Standard Project conditions take place.

- Pessimistic (P): Issues, revisions or setbacks arise.

The expected estimate is calculated using:

Expected Time = (O + 4M + P) / 6

This approach is beneficial due to the unpredictable nature of software development. For instance, specifications might require elaboration, testing could uncover issues, or the client might request extra time to evaluate a feature.

Estimate Table

| Task | O | M | P | Expected Hours |
| --- | --- | --- | --- | --- |
| T1 Requirements | 8 | 10 | 14 | 10.3 |
| T2 Planning | 4 | 6 | 9 | 6.2 |
| T3 Database design | 6 | 8 | 12 | 8.3 |
| T4 Interface design | 5 | 8 | 12 | 8.2 |
| T5 User access | 4 | 6 | 9 | 6.2 |
| T6 Student/fee module | 8 | 12 | 18 | 12.3 |
| T7 Payment module | 12 | 18 | 27 | 18.5 |
| T8 Balance/receipts | 8 | 11 | 16 | 11.3 |
| T9 Search/reports | 8 | 12 | 11 | 7.3 |
| T10 Audit/backup | 5 | 7 | 11 | 7.3 |
| T11 Testing | 12 | 18 | 27 | 18.5 |
| T12 User acceptance | 6 | 8 | 12 | 8.3 |
| T13 Deployment/training | 6 | 8 | 12 | 8.3 |

Total                                                                                           126.0 hours

The estimated effort is approxmatley 126 hours.

The estimate is not presented as an exact prediction. It is a planning estimate based on the defined scope and assumptions.

Estimation Assumptions

The estimate assumes:

- One main developer.

- A small system for approximately 450 students.

- The client provides information and feedback on time.

- The existing laptop and printer can be used.

- No direct bank or mobile-money integration is required.

- No major new requirements are added after approval.

- Staff are available for testing and training.

- No major hardware purchase is required.

- Power interruptions are considered in system testing.

- The project uses the scope defined in this report.

Reasoning

The payment module gets the highest development estimate as it needs to manage cash, bank deposits, mobile transfers, and installment payments.

Testing is also given a high estimate since financial information needs to be precise. Mistakes in balances or receipts may lead to conflicts.
Requirements and design are finalized prior to significant development to ensure that the system aligns with the school's genuine processes.

2.3 Work Schedule

The estimated 126 hours can be organised into an approximately 8-week schedule, assuming the project is carried out part-time and some tasks overlap.

| Week | Work | Client Sees |
| --- | --- | --- |
| 1 | Requirements and SRS | Confirmed requirements and priorities. |
| 2 | Planning, database and interface design | Basic system design and screens. |
| 3 | User access and student/fee module | Login and student records. |
| 4 | Payment module | Payment entry and instalments. |
| 5 | Balance, receipts and search | Balances, receipts and payment history. |
| 6 | Reports, audit and backup | Arrears and management reports. |
| 7 | Testing and corrections | Test version for staff |
| 8 | User acceptance, deployment and training | Working system and trained users. |

Delivery Order

- The tasks are organized in this sequence because certain activities rely on prior activities.

- Requirements should be validated prior to the complete design of the system.

- The design of the database and interface must be finalized prior to the primary development efforts.

- Information about students and fees must be available prior to recording payment transactions.

- Recording payments needs to be finalized prior to producing accurate arrears and reports.

- Testing should take place prior to deployment.

- User acceptance testing must occur prior to the final handover to ensure that the bursar verifies the system aligns with actual school operations.

Main Milestone

Milestone 1: Requirments Approved

The school confirms that the SRS correctly describes the required system.

Milestone 2: Basic Working System

User can log in and manage basic student and fee information.

Milestone 3: Core Fee Tracking Complete

Users can record payments, including instalments, and see outstanding balances.

Milestone 4: Reporting and Receipt Functions Complete

Receipts, arrears and management reports are available.

Milestone 5: Acceptance and Handover

The bursar and office assistants test the system, staff receive training and the system is prepared for normal use.

2.4 Dependency-Triangle Analysis

The project has three important factors:

Scope — Time — Cost

These factors are connected. If one changes, at least one of the other factors normally has to change.

Current Recommended Position

The recommended first release should focus on the Must-have requirements:

- Student fee records.

- Payment recording.

- Cash, bank and mobile-money payments.

- Instalment payments.

- Balance calculation.

- Receipts.

- Student search.

- Payment history.

- Arrears identification.

- Security.

- Backup.

- Basic reporting.

This scope directly addresses the school's main problems.

Advanced features such as charts and automatic integrations should not delay the core system.Option 1 — Keep the Scope and Keep the Quality

Under this option, the school receives the planned first release.

Estimated effort: approximately 126 hours.

Expected schedule: approximately 8 weeks.

Cost: moderate and based mainly on developer effort.

The advantage is that the school receives the important features without deliberately reducing the agreed scope.

This is the recommended option.

Option 2 — Finish Faster

If the school specifies a need for the system in a significantly shorter timeframe, the project might require extra development resources.
For instance, two developers might collaborate on various sections of the system.
Nonetheless, increasing the number of developers does not inherently cut the project duration in half, as certain tasks remain dependent on one another. Additional developers can create more coordination and testing tasks.

This option is likely to increase cost.

The school could also reduce the first-release scope to make the deadline easier to meet.

For example, the first release could delay:

- Charts.

- Advanced report export.

- Some non-essential reporting features.

The core payment and receipt functions would remain.

Option 3 — Reduce Cost

If the school has a strict budget, the project could reduce the number of features in the first release.

The first release could contain only:

- Student records.

- Fee records.

- Payment recording.

- Instalments.

- Balance calculation.

- Receipts.

- Arrears.

- Basic reports.

- Security and backup.

Charts and advanced report functions could be added later.

The disadvantage is that the school would receive fewer features initially.

Another possibility would be to keep the same scope but allow a longer development period.

Dependency-Triangle Comparison

| Option | Scope | Time | Cost |
| --- | --- | --- | --- |
| - Balanced | Core + important features | About 8 weeks | Moderate |
| - Fast delivery | Reduced scope or more developers | Shorter | Higher if extra resources are used |
| - Lower cost | Smaller first release or longer schedule | Longer or reduced features | Lower |

Recommendation

Option 1 is recommended.

The school specifically requires that fee arrears are evident and receipts are reliable. Consequently, the initial release must emphasize precise payment logs, installments, balances, receipts, and outstanding amounts.
Enhanced functionalities must not postpone these essential tasks. They may be included in a subsequent release if the school has more time and funds.
This method offers a suitable equilibrium among scope, time, and cost while minimizing the risk of producing an excessively complex system.

Conclusion

AI Use Declaration: